# Sepsis Sample Biobank Roadmap & SOP

## Purpose

A detailed step-by-step roadmap for planning, collecting, processing, storing, documenting, and using blood samples for sepsis research and future diagnostic development.

# Step 1: Define the Research Goal

## What to do

Clearly define the purpose of sample collection. Examples:

- Build a sepsis biobank

- Develop a SERS diagnostic chip

- Compare biomarkers (CRP, PCT, IL-6)

- Train AI/ML model for sepsis prediction

## Why this step is important

A clear objective determines what samples to collect, what metadata to record, storage conditions, and study design.

## Benefit

Prevents random collection and creates a focused, publishable project.

## Risks if skipped

Unusable samples, missing data, weak publication value.

# Step 2: Literature Review & Gap Analysis

## What to do

Read recent research papers on:

- Sepsis biomarkers

- Blood biobanking

- SERS diagnostics

- Clinical sample handling

- ML in sepsis diagnosis

Create a table of:

- What has been done

- Limitations

- Your novelty

## Why this step is important

Ensures your work solves a real problem and follows accepted scientific standards.

## Benefit

Stronger proposal, easier professor approval, better publication chance.

# Step 3: Build the Study Design

## What to do

Create groups: 1. Confirmed sepsis positive 2. Suspected but negative 3. Healthy / control (if approved)

Define target numbers, e.g. 50 / 50 / 30.

Define primary outcome:

- Can chip distinguish sepsis vs non-sepsis?

## Why this step is important

Good controls are essential for valid results.

## Benefit

Reliable comparisons and stronger statistics.

# Step 4: Ethical & Institutional Approval

## What to do

Prepare documents:

- Study protocol

- Consent form / waiver request

- Data privacy plan

- Biosafety handling plan

- Sample storage plan

Submit to ethics committee / institution / hospital.

## Why this step is important

Human samples cannot be collected informally.

## Benefit

Legal, ethical, and publishable workflow.

## Risks if skipped

Data cannot be used for publication.

# Step 5: Collaborate with Hospital / Clinical Team

## What to do

Identify doctors, ICU staff, microbiology lab, pathology lab. Decide where samples come from and who informs research team.

## Why this step is important

Clinical diagnosis labels come from hospital workflow.

## Benefit

Access to real samples and confirmed reports.

# Step 6: Prepare Infrastructure

## Equipment Needed

- PPE

- Refrigerator (2–8°C)

- Freezer (-20°C)

- Preferred: Ultra-low freezer (-80°C)

- Centrifuge

- Micropipettes

- Cryovials

- Labels / barcode printer

- Biohazard bins

- Laptop with tracker file

## Why this step is important

Without infrastructure, sample quality drops.

# Step 7: Create Sample ID System

## Format

- SEP-001

- SEP-002

- NEG-001

- CTRL-001

## Why this step is important

Protects identity and avoids confusion.

## Benefit

Traceable and anonymized dataset.

# Step 8: Create Data Tracker File

## Recommended Columns

- Sample ID

- Date/time collected

- Age n- Sex

- Ward/ICU

- Sepsis status

- CRP

- PCT

- Culture result

- Tube type

- Plasma stored? (Y/N)

- Freezer location

- Notes

## Why this step is important

A sample without data loses research value.

# Step 9: Patient Screening

## What to do

Identify patients undergoing routine sepsis evaluation. Use inclusion/exclusion criteria.

## Inclusion Example

- Suspected infection

- Sepsis workup ordered

## Exclusion Example

- Insufficient sample

- Wrong label

- Refusal if consent required

## Why this step is important

Prevents poor quality dataset.

# Step 10: Blood Collection Procedure

## Before Collection

- Verify patient ID clinically

- Confirm tube labels ready

- Wear PPE

- Use sterile supplies

## Venipuncture Steps

- Hand hygiene

- Apply gloves

- Apply tourniquet

- Clean site with 70% alcohol

- Allow skin to dry

- Draw blood using sterile needle

- Fill required tubes

- Remove needle safely

- Apply gauze/bandage

- Dispose sharps immediately

## Tube Types

- EDTA tube: plasma biomarkers

- Serum tube: serum biomarkers

- Blood culture bottle: clinical microbiology

## Why this step is important

Proper collection avoids contamination and hemolysis.

# Step 11: Labeling Rules

## Write on Tube

- Sample ID

- Date

- Time

- Sample type

- Initials

Example: SEP-014 | 24-Apr-26 | 10:40 | Plasma

## Why this step is important

Mislabeling can destroy the study.

# Step 12: Transport to Lab

## What to do

Move samples in upright rack / leak-proof container. Process within 2 hours when possible.

## Why this step is important

Delay can degrade biomarkers.

# Step 13: Processing Samples

## Plasma

- Invert EDTA tube gently 8–10 times

- Centrifuge 1500–2000 g for 10 min

- Transfer plasma top layer carefully

## Serum

- Allow clotting 20–30 min

- Centrifuge 1500–2000 g for 10 min

- Transfer serum carefully

## Why this step is important

Separates usable biomarker-rich fraction.

# Step 14: Aliquoting

## What to do

Split into small cryovials:

- 0.5 mL x 4 or 1 mL x 3

## Why this step is important

Avoid repeated freeze-thaw damage.

## Benefit

Multiple future experiments from one patient.

# Step 15: Storage Conditions

## Recommended

- Whole blood: temporary 2–8°C only

- Plasma/Serum short term: -20°C

- Long term: -80°C best

## Why this step is important

Low temperature preserves proteins and analytes.

# Step 16: Freezer Mapping

## Example

Freezer 1 > Rack B > Box 03 > Position D6

Record exact location in tracker.

## Why this step is important

Saves time and prevents lost samples.

# Step 17: Save Clinical Reports Securely

## What to do

Store anonymized digital reports in folders:

- /Reports/Positive/

- /Reports/Negative/

- /Reports/Controls/

Use Sample ID filenames. Example: SEP-014.pdf

## Why this step is important

Reports validate diagnosis labels.

# Step 18: Data Security

## Rules

- Password protect files

- Backup regularly

- Restrict access

- Keep ID link file separately

## Why this step is important

Protects privacy and research integrity.

# Step 19: Quality Control

## Monthly Checks

- Freezer temperature logs

- Inventory audit

- Label readability

- Missing metadata review

- Sample condition check

## Why this step is important

Biobanks fail without maintenance.

# Step 20: Future Testing Workflow

When chip is ready: 1. Select balanced positives/negatives 2. Retrieve one aliquot each 3. Run blinded testing 4. Compare with clinical diagnosis 5. Analyze sensitivity/specificity 6. Publish results

# Common Drawbacks & Solutions

## Hemolysis

Cause: rough collection/shaking Fix: gentle handling

## Missing Labels

Fix: label before collection

## Freeze-Thaw Damage

Fix: aliquot small volumes

## No Controls

Fix: collect negative/control groups too

## Incomplete Metadata

Fix: mandatory tracker fields

## Sample Loss

Fix: freezer map + backups

# Recommended Initial Milestone (6 Months)

- 50 Positive

- 50 Negative

- 30 Control

- Complete metadata for >90%

- Stable freezer logs

# Final Goal

Create a trusted sepsis sample repository enabling diagnostics, publications, ML models, and translation into hospital-ready technology.